8-Week Delivery Plan Explained

The objective of this plan is to deliver three features while maintaining quality through structured testing, regression, user acceptance testing (UAT), and release preparation.

Weeks 1–2: Build Feature A

The team starts by focusing on Feature A.

During the first two weeks we:

- Gather any final requirements

- Complete development

- Perform developer testing

- Prepare the feature for formal QA

The goal is to get the first major piece of functionality built and stable as early as possible.

Weeks 2–3: Build Feature B

While Feature A moves into testing, development begins on Feature B.

This allows the team to work efficiently in parallel rather than waiting for Feature A to complete completely.

By the end of Week 3:

- Feature A is entering testing

- Feature B development is largely complete

Weeks 3–5: Testing and Fixing

Once Feature A is developed:

Week 3

Feature A enters formal testing.

The QA team validates:

- Functional requirements

- User journeys

- Edge cases

- Integration points

Week 4

Any issues found are fixed.

Week 5

Retesting confirms the fixes work correctly and have not introduced new defects.

The same process then follows for Feature B shortly afterwards.

Weeks 4–5: Buffer and Spillover

Projects rarely run exactly to plan.

The buffer built into the schedule provides protection against:

- Delayed requirements

- Unexpected technical complexity

- Resource constraints

- Production support interruptions

Instead of immediately impacting delivery dates, the project can absorb small delays here.

Weeks 5–6: Feature C Development

Feature C is intentionally scheduled later.

This provides flexibility because:

- Requirements may still be evolving

- It is lower priority

- Lessons learned from Features A and B can be applied

The team uses the buffer period and then develops Feature C in Weeks 5 and 6.

Weeks 4–7: Regression Testing

Regression testing runs across multiple weeks.

The purpose is to ensure that:

- New changes do not break existing functionality

- Features work together correctly

- Integrations remain stable

This is particularly important when multiple features are being delivered in the same release.

Think of regression testing as the project's safety net.

Weeks 6–7: UAT and Hardening

After development and regression testing are complete, the project moves into:

User Acceptance Testing (UAT)

Business users validate that:

- The solution meets business needs

- Workflows function correctly

- Reporting and integrations behave as expected

Hardening

The technical team focuses on:

- Performance improvements

- Security reviews

- Stability improvements

- Production readiness

The objective is to remove any remaining risk before release.

Week 8: Release Preparation

The final week is reserved for deployment readiness.

Activities include:

- Release documentation

- Deployment planning

- Rollback planning

- Final approvals

- Release communications

No major development should occur during this stage.

The focus is entirely on delivering safely.

End of Week 8: Go Live